School of Engineering Technology and Applied Science

Information and Communication Engineering Technology

Software Development Project II (COMP313)

Project Planning and Management
for 1st Release

Team 6 – Booking Platform

Minh Lieu

Yehong Hu

Larry Yu

Neil

Eldin

Nforne Martin

tamm

Professor: Jin Li

February 2026

# Table of Contents

1.0  Release Plans for 1st and 2nd Release

1.1  Project Overview and Development Approach

1.2  Iteration Length and Team Capacity

1.3  Release 1 Plan (1st Software Release)

1.4  Release 2 Plan (2nd Software Release)

2.0  1st and 2nd Iteration Planning for 1st Release

2.1  Iteration 1 Planning

2.2  Iteration 2 Planning

References

# 1.0  Release Plans for 1st and 2nd Release

## 1.1  Project Overview and Development Approach

The Booking Platform is a web-based local service marketplace that connects service seekers with local service providers through a competitive bidding and scheduling system. The project follows an Agile development methodology with iterative releases to deliver incremental value. The development is organized into two major software releases, each consisting of two iterations (sprints), for a total of four iterations across the project lifecycle.

The product development roadmap is structured around the following themes for each release:

Release 1 – Core Booking Workflow: Establish the foundational end-to-end booking process, including user authentication, service request creation, provider bidding, booking confirmation with automatic calendar blocking, and basic administrative oversight. This release delivers the minimum viable product (MVP) that demonstrates the platform's primary value proposition.

Release 2 – Enhanced User Experience and Platform Management: Build upon the core workflow with features that improve usability, trust, and administrative capabilities, including booking history, ratings and reviews, account management for all user roles, provider availability management, and administrative reporting.

## 1.2  Iteration Length and Team Capacity

Each iteration has a fixed length of 14 days (2 weeks). The team consists of five developers with varying expertise in frontend development (React), backend development (Node.js/Express), database design (MongoDB), and testing. The team's combined velocity is estimated at approximately 23 story points per iteration based on the Wide-Band Delphi estimation method.

| Parameter | Value | Notes |
| --- | --- | --- |
| Iteration Length | 14 days (2 weeks) | Consistent across all iterations |
| Team Size | 5 developers | Cross-functional team |
| Estimated Velocity | ~23 story points/iteration | Based on Wide-Band Delphi |
| Total Iterations | 4 (2 per release) | 2 releases planned |
| Estimation Scale | 1, 3, 5, 8 | Increasing complexity/effort |

Table 1: Team Capacity and Iteration Parameters.

## 1.3  Release 1 Plan (1st Software Release)

Release 1 focuses on delivering the core booking workflow that forms the foundation of the platform. The stories selected for this release represent the Must-Have features identified through MoSCoW prioritization. These stories establish the end-to-end process from user registration through service request creation, provider bidding, booking confirmation, and basic administrative management. The release date for Release 1 is February 9, 2026.

Release 1 Date: February 9, 2026

Total Story Points: 46

| Iteration 1 (Jan 13 – Jan 26, 2026) | Iteration 2 (Jan 27 – Feb 9, 2026) |
| --- | --- |
| As a Customer, I can register an account with my name, email, password, and role so that I can access the booking platform. [5 pts] | As a Service Provider, I can submit a bid with price and message on an open service request so that the customer can consider my offer. [8 pts] |
| As a User, I can log in with my email and password so that I can access my personalized dashboard. [5 pts - included in registration story] | As a Customer, I can view all bids submitted on my service request and compare provider prices. [3 pts] |
| As a Customer, I can create a service request with title, type, description, location, and preferred time so that providers can bid. [5 pts] | As a Customer, I can accept a bid to confirm a booking so that the provider's calendar is automatically blocked. [8 pts] |
| As a Service Provider, I can register and set up my profile with bio and service types so that customers can learn about my qualifications. [5 pts] | As an Admin, I can view the platform dashboard with statistics so that I can monitor platform activity. [3 pts] |
| As a Service Provider, I can browse all open service requests so that I can find jobs matching my skills. [3 pts] | As an Admin, I can view, update, and delete user accounts so that I can manage platform users. [3 pts] |
|  | As an Admin, I can view and delete user reviews so that I can moderate inappropriate content. [3 pts] |
|  | As a Provider, I can manage my availability calendar by creating, updating, and deleting time slots. [3 pts] |
| Iteration 1 Total: 23 story points | Iteration 2 Total: 23 story points |

Table 2: Release 1.0 Plan – Stories allocated to Iteration 1 and Iteration 2.

The allocation of stories across the two iterations reflects the team's development strategy: Iteration 1 focuses on establishing the user authentication system and the service request pipeline (registration, login, service creation, provider setup, and browsing requests), while Iteration 2 builds upon this foundation to complete the bidding, booking confirmation, calendar blocking, and administrative features. This sequencing ensures that dependent features are developed in the correct order and that the team can integrate and test incrementally.

The distribution of 23 story points per iteration realistically reflects the team's capacity, ensuring that developers are not over-committed while maintaining a consistent development pace. The team's strengths in full-stack JavaScript development (React frontend, Node.js/Express backend, MongoDB database) allow for efficient parallel development of frontend and backend components.

## 1.4  Release 2 Plan (2nd Software Release)

Release 2 focuses on enhancing the platform with features that improve user experience, trust, and administrative capabilities. The stories selected for this release represent the Should-Have features identified through MoSCoW prioritization. These features depend on the successful implementation of the core booking workflow delivered in Release 1. The release date for Release 2 is March 9, 2026 (end of semester, fixed date).

Release 2 Date: March 9, 2026 (Fixed – End of Semester)

Total Story Points: 31

| Iteration 3 (Feb 10 – Feb 23, 2026) | Iteration 4 (Feb 24 – Mar 9, 2026) |
| --- | --- |
| As a Customer, I can view my booking status and history so that I can track past and current bookings. [3 pts] | As a Service Provider, I can view my past bookings and history so that I can track completed services. [3 pts] |
| As a Customer, I can rate and review a service provider after service completion so that future customers can make informed decisions. [3 pts] | As a Service Provider, I can manage my account information so that I can update my profile and service details. [3 pts] |
| As a Customer, I can manage my account information so that I can update my profile details. [3 pts] | As an Admin, I can moderate reviews and ratings so that I can maintain platform quality. [3 pts] |
| As a Service Provider, I can manage my availability schedule so that customers know when I am available. [5 pts] | As an Admin, I can view basic reports on platform usage so that I can make data-driven decisions. [5 pts] |
|  | As an Admin, I can manage my account information so that I can update administrative settings. [3 pts] |
| Iteration 3 Total: 14 story points | Iteration 4 Total: 17 story points |

Table 3: Release 2.0 Plan – Stories allocated to Iteration 3 and Iteration 4.

Release 2 carries a lower total story point count (31 points) compared to Release 1 (46 points), reflecting the reduced complexity of enhancement features relative to core infrastructure. Iteration 3 focuses on customer-facing enhancements (booking history, ratings, account management) and provider availability management, while Iteration 4 addresses provider-side enhancements, administrative reporting, and review moderation. This distribution ensures that customer-facing improvements are delivered first, allowing for user feedback before the final iteration.

The lighter workload in Release 2 also provides buffer time for addressing any technical debt or bugs discovered during Release 1, ensuring that the platform remains stable and reliable as new features are added.

# 2.0  1st and 2nd Iteration Planning for 1st Release

This section presents the detailed iteration planning for the 1st Software Release. Each story assigned to an iteration is disaggregated into its constituent development tasks. For each task, the estimated effort (in hours), the responsible developer, and a brief description are provided. Task estimation was performed collaboratively during iteration planning meetings, where developers accepted responsibility for tasks based on their expertise and availability.

The estimation unit used is developer-hours. Tasks are estimated consistently using the following guidelines: small tasks (1–2 hours) involve simple CRUD operations or basic UI components; medium tasks (3–4 hours) involve moderate business logic or complex UI; large tasks (5–8 hours) involve complex integrations, multi-step workflows, or comprehensive testing.

## 2.1  Iteration 1 Planning

Iteration 1: January 13 – January 26, 2026

Total Story Points: 23

Iteration 1 establishes the foundational components of the platform: user authentication (registration and login), service request creation, provider profile setup, and the ability for providers to browse open service requests. These stories form the prerequisite for the bidding and booking features planned for Iteration 2.

Story 1: User Registration

"As a Customer, I can register an account with my name, email, password, and role so that I can access the booking platform and post service requests."

Estimated Story Points: 5

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T1.1 | Create User.model.js with Mongoose schema (name, email, password, role, bio, serviceTypes, phone, isActive, timestamps) | 3 | Minh Lieu |
| T1.2 | Implement password hashing using bcrypt in User model pre-save hook | 2 | Minh Lieu |
| T1.3 | Create auth.controller.js register function with input validation, duplicate email check, and JWT token generation | 4 | Team Member 2 |
| T1.4 | Create auth.routes.js with POST /api/auth/register route and express-validator middleware | 2 | Team Member 2 |
| T1.5 | Create validators.js with reusable validation rules for registration inputs | 2 | Team Member 2 |
| T1.6 | Create Register.jsx frontend page with form (name, email, password, role selector) | 4 | Team Member 3 |
| T1.7 | Create auth.api.js with register API call using Axios | 1 | Team Member 3 |
| T1.8 | Write unit tests for registration endpoint (valid registration, duplicate email, invalid email, short password) | 3 | Team Member 4 |
| T1.9 | Configure MongoDB Atlas connection in config/db.js and environment variables in config/env.js | 2 | Minh Lieu |

Table 4: Disaggregated tasks for Story 1 – User Registration.

Story 2: User Login

"As a User, I can log in with my email and password so that I can access my personalized dashboard and features."

Estimated Story Points: 5 (combined with registration story)

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T2.1 | Implement login function in auth.controller.js with email lookup, bcrypt password comparison, and JWT generation | 3 | Minh Lieu |
| T2.2 | Create auth.middleware.js to verify JWT tokens from Authorization header | 3 | Minh Lieu |
| T2.3 | Create role.middleware.js to check user role against allowed roles | 2 | Team Member 2 |
| T2.4 | Implement getMe and updateProfile functions in auth.controller.js | 2 | Team Member 2 |
| T2.5 | Create Login.jsx frontend page with email/password form and error handling | 3 | Team Member 3 |
| T2.6 | Create AuthProvider.jsx context for managing authentication state (token, user, login/logout) | 4 | Team Member 3 |
| T2.7 | Create useAuth.js custom hook and RequireAuth.jsx / RequireRole.jsx route guards | 3 | Team Member 5 |
| T2.8 | Write unit tests for login endpoint (valid login, wrong password, non-existent email) | 2 | Team Member 4 |
| T2.9 | Create Navbar.jsx component with conditional rendering based on authentication state and user role | 3 | Team Member 5 |

Table 5: Disaggregated tasks for Story 2 – User Login.

Story 3: Create Service Request

"As a Customer, I can create a service request with title, type, description, location, and preferred time so that local service providers can view and bid on my request."

Estimated Story Points: 5

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T3.1 | Create Service.model.js with Mongoose schema (title, serviceType, description, location, preferredTime, customer, status, bids subdocument, selectedProvider) | 4 | Team Member 3 |
| T3.2 | Implement createService function in services.controller.js with input validation | 3 | Team Member 4 |
| T3.3 | Implement getServices function with filtering (serviceType, status), search, and pagination | 3 | Team Member 4 |
| T3.4 | Create services.routes.js with POST /api/services and GET /api/services routes | 2 | Team Member 3 |
| T3.5 | Create NewRequest.jsx frontend page with form for title, service type dropdown, description, location, and date/time picker | 4 | Team Member 5 |
| T3.6 | Create services.api.js with createService and getServices API calls | 2 | Team Member 5 |
| T3.7 | Create Customer Dashboard.jsx with summary cards and link to create new request | 3 | Team Member 3 |
| T3.8 | Write acceptance tests for service creation (valid creation, no auth, missing fields) | 2 | Team Member 4 |

Table 6: Disaggregated tasks for Story 3 – Create Service Request.

Story 4: Provider Registration and Profile Setup

"As a Service Provider, I can register an account and set up my profile with bio and service types so that customers can learn about my qualifications."

Estimated Story Points: 5

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T4.1 | Extend User model to support provider-specific fields (bio, serviceTypes array, phone) | 2 | Minh Lieu |
| T4.2 | Implement updateProfile function in auth.controller.js with field whitelisting for provider profile updates | 3 | Team Member 2 |
| T4.3 | Create Provider Dashboard.jsx with profile summary, stats cards, and quick action links | 4 | Team Member 5 |
| T4.4 | Implement profile editing UI in Provider Dashboard with bio, service types, and phone fields | 3 | Team Member 5 |
| T4.5 | Write acceptance tests for provider registration and profile update | 2 | Team Member 4 |

Table 7: Disaggregated tasks for Story 4 – Provider Registration and Profile Setup.

Story 5: View Open Service Requests

"As a Service Provider, I can browse all open service requests so that I can find jobs that match my skills and submit bids."

Estimated Story Points: 3

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T5.1 | Implement getServiceById function in services.controller.js with populated bids and provider details | 2 | Team Member 4 |
| T5.2 | Create MyServices.jsx (Provider) page to display all open service requests with filtering by service type | 4 | Minh Lieu |
| T5.3 | Create ServiceCard.jsx reusable component to display service request summary (title, type, location, time, bid count) | 3 | Team Member 5 |
| T5.4 | Create ServiceDetail.jsx page showing full request details and list of existing bids | 3 | Team Member 3 |
| T5.5 | Create Services.jsx (Public) page for browsing all services with search and filter functionality | 3 | Minh Lieu |
| T5.6 | Write acceptance tests for viewing open requests (list all, filter by type) | 2 | Team Member 4 |

Table 8: Disaggregated tasks for Story 5 – View Open Service Requests.

Iteration 1 Summary

| Developer | Tasks Assigned | Total Estimated Hours | Primary Responsibilities |
| --- | --- | --- | --- |
| Minh Lieu | 6 tasks | 15 hrs | User model, auth backend, DB config, provider browsing UI |
| Team Member 2 | 5 tasks | 11 hrs | Auth controller, routes, validators, role middleware |
| Team Member 3 | 5 tasks | 14 hrs | Register/Login UI, Service model, routes, ServiceDetail page |
| Team Member 4 | 6 tasks | 11 hrs | Services controller, unit tests, acceptance tests |
| Team Member 5 | 6 tasks | 16 hrs | Auth hooks, route guards, Navbar, Provider Dashboard, ServiceCard |

Table 9: Iteration 1 – Developer workload summary.

The workload distribution across Iteration 1 is balanced, with each developer contributing between 11 and 16 estimated hours over the 14-day iteration. Task ownership is consistent, with each developer focusing on their area of expertise: Minh Lieu and Team Member 2 handle backend development, Team Member 3 and Team Member 5 focus on frontend development, and Team Member 4 leads testing efforts while contributing to backend controller development.

## 2.2  Iteration 2 Planning

Iteration 2: January 27 – February 9, 2026

Total Story Points: 23

Iteration 2 builds upon the foundation established in Iteration 1 to complete the core booking workflow. This iteration implements the bidding system, booking confirmation with automatic calendar blocking, bid comparison for customers, and the administrative management features (dashboard, user management, review moderation, and provider availability management). These stories complete the end-to-end booking process and deliver the 1st Software Release.

Story 6: Submit Bid on Service Request

"As a Service Provider, I can submit a bid with price and message on an open service request so that the customer can consider my offer."

Estimated Story Points: 8

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T6.1 | Implement submitBid function in services.controller.js with duplicate bid prevention and status validation | 4 | Team Member 3 |
| T6.2 | Add bid subdocument schema to Service model (provider, price, message, createdAt) | 2 | Minh Lieu |
| T6.3 | Create POST /api/services/:id/bids route with authentication and provider role check | 2 | Team Member 2 |
| T6.4 | Create BookingForm.jsx component for providers to submit bids (price input, message textarea) | 3 | Team Member 5 |
| T6.5 | Update ServiceDetail.jsx to show bid submission form for authenticated providers | 3 | Team Member 5 |
| T6.6 | Write acceptance tests for bid submission (valid bid, duplicate bid, non-open request) | 3 | Team Member 4 |

Table 10: Disaggregated tasks for Story 6 – Submit Bid on Service Request.

Story 7: View Bids and Compare

"As a Customer, I can view all bids submitted on my service request and compare provider prices and messages so that I can choose the best provider."

Estimated Story Points: 3

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T7.1 | Implement getMyRequests function in services.controller.js to return customer's requests with populated bids | 2 | Team Member 4 |
| T7.2 | Update ServiceDetail.jsx to display bids list with provider name, bio, price, message, and "Accept Bid" button for the customer | 4 | Team Member 3 |
| T7.3 | Create MyBookings.jsx (Customer) page to list all service requests with bid counts and status | 3 | Team Member 3 |
| T7.4 | Write acceptance tests for viewing bids (populated bids, customer's own requests) | 2 | Team Member 4 |

Table 11: Disaggregated tasks for Story 7 – View Bids and Compare.

Story 8: Confirm Booking (Accept Bid) with Calendar Blocking

"As a Customer, I can accept a bid on my service request to confirm a booking so that the provider's calendar is automatically blocked to prevent double bookings."

Estimated Story Points: 8

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T8.1 | Create Booking.model.js with Mongoose schema (service, customer, provider, scheduledTime, price, status, rating) | 3 | Minh Lieu |
| T8.2 | Create Availability.model.js with schema (provider, date, startTime, endTime, isBlocked, bookingRef) | 2 | Minh Lieu |
| T8.3 | Implement createBooking function in bookings.controller.js with bid validation, conflict checking, booking creation, service status update, and calendar blocking | 6 | Team Member 2 |
| T8.4 | Create bookings.routes.js with POST /api/bookings route | 2 | Team Member 2 |
| T8.5 | Implement updateBookingStatus function with valid status transitions (pending→confirmed→completed/cancelled) | 4 | Team Member 2 |
| T8.6 | Create BookingDetail.jsx (Customer) page showing booking details, status, and provider info | 3 | Team Member 5 |
| T8.7 | Create bookings.api.js with createBooking, getMyBookings, and updateBookingStatus API calls | 2 | Team Member 5 |
| T8.8 | Write acceptance tests for booking confirmation (valid booking, already booked, scheduling conflict) | 3 | Team Member 4 |

Table 12: Disaggregated tasks for Story 8 – Confirm Booking with Calendar Blocking.

Story 9: Admin Dashboard and Statistics

"As an Admin, I can view the platform dashboard with statistics so that I can monitor overall platform activity and health."

Estimated Story Points: 3

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T9.1 | Implement getStats function in admin.controller.js with aggregated counts (users, services, bookings by status) | 3 | Team Member 2 |
| T9.2 | Create admin.routes.js with GET /api/admin/stats route protected by admin role middleware | 1 | Team Member 2 |
| T9.3 | Create Admin Dashboard.jsx page with statistics cards (total users, providers, services, bookings) | 3 | Team Member 3 |
| T9.4 | Write acceptance tests for admin stats endpoint (admin access, non-admin rejection) | 2 | Team Member 4 |

Table 13: Disaggregated tasks for Story 9 – Admin Dashboard and Statistics.

Story 10: Admin User Management

"As an Admin, I can view, update, and delete user accounts so that I can manage the platform users and maintain quality."

Estimated Story Points: 3

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T10.1 | Implement getAllUsers, getUserById, updateUser, and deleteUser functions in admin.controller.js | 4 | Team Member 2 |
| T10.2 | Create admin routes for user management (GET, PUT, DELETE /api/admin/users) | 2 | Team Member 2 |
| T10.3 | Create Admin Users.jsx page with user list table, role filter, activate/deactivate toggle, and delete button | 4 | Team Member 3 |
| T10.4 | Write acceptance tests for user management (list by role, deactivate user, delete user, prevent admin deletion) | 3 | Team Member 4 |

Table 14: Disaggregated tasks for Story 10 – Admin User Management.

Story 11: Ratings and Review Moderation

"As an Admin, I can view and delete user reviews so that I can moderate inappropriate content and maintain platform trust."

Estimated Story Points: 3

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T11.1 | Implement submitRating function in bookings.controller.js (score, comment, completed-only, no duplicates) | 3 | Minh Lieu |
| T11.2 | Implement getAllReviews and deleteReview functions in admin.controller.js | 3 | Team Member 2 |
| T11.3 | Create Admin Providers.jsx (Reviews) page with review list, rating display, and delete button | 3 | Team Member 5 |
| T11.4 | Write acceptance tests for review moderation (list reviews, delete review) | 2 | Team Member 4 |

Table 15: Disaggregated tasks for Story 11 – Ratings and Review Moderation.

Story 12: Provider Availability Management

"As a Service Provider, I can manage my availability calendar by creating, updating, and deleting time slots so that customers know when I am available."

Estimated Story Points: 3

| Task | Description | Estimate (hrs) | Developer |
| --- | --- | --- | --- |
| T12.1 | Implement createAvailability, getMyAvailability, updateAvailability, and deleteAvailability functions in availability.controller.js with overlap detection and blocked-slot protection | 5 | Minh Lieu |
| T12.2 | Create availability.routes.js with CRUD routes and provider role middleware | 2 | Minh Lieu |
| T12.3 | Create Availability.jsx (Provider) page with calendar view, add/edit/delete time slot forms | 4 | Team Member 5 |
| T12.4 | Write acceptance tests for availability management (create slot, overlapping slot, invalid time range) | 2 | Team Member 4 |

Table 16: Disaggregated tasks for Story 12 – Provider Availability Management.

Iteration 2 Summary

| Developer | Tasks Assigned | Total Estimated Hours | Primary Responsibilities |
| --- | --- | --- | --- |
| Minh Lieu | 6 tasks | 16 hrs | Booking/Availability models, bid schema, availability controller, rating logic |
| Team Member 2 | 7 tasks | 16 hrs | Booking controller, admin controller, routes, status transitions |
| Team Member 3 | 4 tasks | 14 hrs | Bid submission controller, bid comparison UI, admin dashboard/users UI |
| Team Member 4 | 7 tasks | 17 hrs | Acceptance tests for all Iteration 2 stories, my-requests controller |
| Team Member 5 | 5 tasks | 13 hrs | BookingForm, BookingDetail, Availability UI, review moderation UI |

Table 17: Iteration 2 – Developer workload summary.

The workload distribution in Iteration 2 is balanced across all five developers, with estimated hours ranging from 13 to 17 hours per developer over the 14-day iteration. Task ownership remains consistent with Iteration 1: backend developers (Minh Lieu, Team Member 2) handle model creation and controller logic, frontend developers (Team Member 3, Team Member 5) build the user interface components, and Team Member 4 continues to lead testing efforts. This consistency ensures that developers build upon their existing knowledge of the codebase and reduces context-switching overhead.

The combined effort across both iterations totals approximately 143 developer-hours for Release 1, which is realistic for a five-person team working over four weeks. The task estimates account for development, testing, code review, and integration activities, ensuring that the team can deliver a complete and tested 1st Software Release by the February 9, 2026 release date.

# References

[1] Cohn, Mike. 2004. User Stories Applied: For Agile Software Development, Addison-Wesley Professional.

[2] Beck, Kent. 1999. Extreme Programming Explained: Embrace Change, Addison-Wesley Professional.

[3] Schwaber, Ken and Sutherland, Jeff. 2020. The Scrum Guide. Scrum.org.